## 1. Intro
Purpose of this document
This is a framework and database meant to guide the monitoring of Dignitas's LeadNow App.
What are the goals of monitoring?
1 | Deliver a better project
Good monitoring can directly improve the delivery of a project. At its best, monitoring serves as a feedback loop that directly informs decision-making throughout a project. It is not an activity done in parallel to programme delivery, it is part of delivery itself.
Monitoring can do this by creating formal checkpoints for the team to pause, pay attention to key questions, collect information and have conversations in answer to those questions, and then make programmatic course corrections as a result. Each monitoring question should have a clear purpose that the team thinks will help them achieve the objectives of the project. Monitoring should not just become a box-ticking exercise that consumes scarce time.
2 | Learning
Monitoring can lead to multiple kinds of learning. Monitoring questions can push the team to examine their work more closely, and therefore help the team learn whether a certain approach is working.
Monitoring data can feed into evaluation exercises of the project.
3 | Accountability
Any reporting requirements should be kept in mind when designing the monitoring database so that the data captured in response to the monitoring questions will facilitate reporting.
Components of this document
1 | Introduction
This first tab provides a definition of monitoring and outlines its main purposes. It also provides an overview of the structure of this document.
2 | Overarching questions and ToC
The second tab in this document presents the high-level (overarching) questions that underpin each of the main sections of the theory of change (i.e. input/resources, activities, outputs, outcomes, enablers/critical factors). These overarching questions are meant to guide the development of more specific monitoring questions that will require specific data to answer.
3 | Monitoring universe
The third tab in this document presents a comprehensive breakdown of the universe of the possible monitoring questions, data sources and indicators that could in theory be targeted by the project monitoring in order to probe each of the components of the theory of change and guide any implementation adaptations, as well as provide data and insights for an eventual evaluation of the impact of the project.
It is often not possible or practical to pursue all the monitoring questions so strategic decision must be made regarding the key questions that will be the focus of the monitoring activities.
4 | Monitoring plan
The fourth tab in this document consists of the monitoring plan and database for the project. It contains only the key questions selected from the monitoring universe as the questions that will be the focus of all monitoring activities.
The monitoring plan specifies the data source (where the data will come from) as well as the indicators (the data points that will be analysed) to be used to answer the key questions.
The monitoring plan also identifies the person responsible for the monitoring activities associated with each question, along with the frequency of monitoring.
Finally, the tab can be used as a database where the monitoring data is recorded according to the frequency specified. This enables all monitoring data to be stored in one location, facilitating its analysis and eventually reporting.
5 | Data Sources
The final tab has a list of (eventually) finalised data sources and the target group. It is also useful for assessing the feasibility of the monitoring plan.

## 2. Overarching Questions & ToC
This list of questions supports the design of this monitoring databse by providing the team with a shared reference point to make sure data is captured on all the different things that should be monitored for the project.
Overarching monitoring questions | Input / | Activities | Ouputs | Outcomes | Goals | Critical factors / enablers
resources
Is the workplan realistic in terms of budget and staff time? | ✓
Are activities happening as planned? |  | ✓
Are activities leading to the expected outputs? |  | ✓ | ✓
Are activities leading to the expected outcomes? |  | ✓ |  | ✓
Are the short-term outcomes leading to the expected goals? |  |  |  | ✓ | ✓
Are the enabling factors in place? Are there derailing factors? | [5 empty] | ✓
How does the changing context affect our workplan? Should the workplan be changed according to changes in context? | [5 empty] | ✓

## 3. Monitoring Universe
| Theory of Change | Monitoring Questions | Purpose / Rationale | Success Criteria | Data Sources
Overarching Questions | Add all statements from the theory of change (excluding the goals beyond the accountability line) | What do we want to reflect upon? | Why are we asking this question? | What are we aiming for? What does 'success' look like in this area? | Where will we look for data/information that helps us answer the question? What is useful, realistic, and within budget?
Activities
Are activities happening as planned?
Mechanisms for Change
Are activities happening as planned?
Enabling Factors
Are the enabling factors in place?
Outputs
Are activities leading to the expected outputs? | Example: Instructional Leaders are enthusiastic about enhancing FLN skills… | To what extent do instructional leaders exhibit positive attitudes towards learning FLN skills? | To understand whether the app’s content and learning are positively received by leaders. | The great majority of leaders show positive attitudes towards learning skills for improving FLN. | Survey
Outcomes
Are activities leading to the expected outcomes? | Example: Teachers will review and use learner data to adjust teaching processes​ | To what extent do teachers use learner data to adjust teaching processes? | To assess whether the app leads to behaviour changes in teachers’ practices around assessment-informed practices. | Following the programme, at least 25% of teachers display assessment-informed practices and this increases over six months. | Lesson observations
Goals
Are the outcomes leading to the expected goals?
Note: Goals beyond the accountability line are not included in the monitoring universe.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would recommend having different questions for each of the components for testing - and pulling these through to the enabling factors, outputs, ST outcomes and MT goals. I also would recommend including some broader questions that are not component specific.

## 4. Monitoring Plan
Theory of Change | Monitoring Questions | Purpose / Rationale | Success Criteria | Data Sources | Indicators | Timing / Frequency | Owner | Starting Point / Baseline | Note: The columns to the right can be used as a database to record the data for each monitoring question and according to the timing/frequency indicated.
Activities
Mechanisms for Change
Enabling Factors
Outputs
Example: Instructional Leaders are enthusiastic about enhancing FLN skills… | To what extent do instructional leaders exhibit positive attitudes towards learning FLN skills? | To understand whether the app’s content and learning are positively received by leaders. | The great majority of leaders show positive attitudes towards learning skills for improving FLN. | Survey | Average proportion of leaders showing positive attitudes on survey items related to learning FLN skills and concepts. | - Halfway through the program - At the end of the program | {add name or team} | n/a
Outcomes
Example: Teachers will review and use learner data to adjust teaching processes​ | To what extent do teachers use learner data to adjust teaching processes? | To assess whether the app leads to behaviour changes in teachers’ practices around assessment-informed practices. | Following the programme, at least 25% of teachers display assessment-informed practices and this increases over six months. | Lesson observations | Average proportion of teachers who use learner data to adjust their practice. | - At the start of the programme - 2-3 months after the programme - 6 months after the programme | {add name or team} | {insert baseline measure}
Term Goals
Note: Goals beyond the accountability line are not included in the monitoring universe.

## 5. Data Sources
No. | Data Sources | Target Group | Owner
1 | Example: Online teacher survey | Teachers | Nancy
2
3
4
5
6
7
8
9